MG ROBERT M. JOYCE

SCHOOL FOR FAMILY AND MORALE, WELFARE AND RECREATION

2280 SIGNAL ROAD, BUILDING 4022

FORT SAM HOUSTON, TX  78234

ONLINE COURSE DEVELOPMENT & MANAGEMENT

- PURPOSE.  This Standing Operating Procedure (SOP) prescribes procedures for

the development and management of courses available online at www.imcomacademy.com.

- REFERENCES.

  - School for FMWR Goals and Objectives

  - IMCOM Regulation 350-1, IMCOM Training and Leader Development, 1 June 2010

- APPLICABILITY. This SOP applies to G7 School for Family and MWR personnel, G9 personnel, and others involved in the development and management of the School for Family and MWR online courses.

# POLICY AND PROCEDURES:

a.  Annually, the School for Family and MWR - Branch Chiefs will request that G9

Program Managers, Region and Garrison staff identify and prioritize training requirements

for the following FY, including online course requests.  The Professional Development

Program (PDP), G9 Program Managers, Region and Garrison staff will be used to drive

and confirm need for new training requests.

b.  Once all requests for online training have been submitted from external and

internal sources,  School employees will determine need and feasibility of such projects

based on PDP review of current learning elements associated to new training request

competencies, -budget, manpower, and other resources. Those courses meeting select

criteria will be approved for inclusion in the School for Family and MWR staff workload.

c.  The School for Family and MWR will initiate approved training projects using the

widely recognized ADDIE instructional design model. The five phases of the ADDIE

Model are:  Analysis, Design, Development, Implementation, and Evaluation.  (see Appendix 1)

1.  ADDIE Phase 1: Course Analysis - Identify the Training Need

    - Designer(s) –a School for Family and MWR staff member will be identified as the

primary course lead/designer. Until the end of the pilot stage, this staff member will be the Project Manager (Primary Pre-hand Off).

    - Course Manager – A School for Family and MWR Academy staff member will

be identified as the primary course manager.  This staff member will be the Project Manager/Course Manager after the initial pilot stage.

    - Subject Matter Experts (SME) – The Subject matter expert will provide

content input and critical review.

    - Course Accreditation liaison- A School for Family and MWR staff member responsible for coordinating course accreditation will be part of the project team.

E.  During the Analysis Phase, the Project Team will:

- Establish the project plan

- Identify new behavior outcomes

- Determine the course delivery method (i.e.: Online Course; Blended Course)

- Establish milestones and timelines

- Set up a wiki space for Project Team collaboration and record keeping

- Gain concurrence from the G9 program proponent

F. The Project Manager will establish the “Online Course Project Planner” for the

identified course (See Appendix 2). The Project team will document on planner as

project progresses. Planner includes sections for:

  - Overview notes on course scope; initial ideas

  - List of project team members and contact info

  - Kick-off Meeting: Date, time, location, agenda

  - Course Goals & Objectives & evaluation method

  - Needs Assessment

  - Course Content ideas

  - Milestones and major target dates

G.  Project Manager arranges a “Kick-Off” Meeting (part analysis, part design). The

purpose of this meeting is to bring ALL team members together to come to initial

agreements.

- Set up in depth meeting with the SME.  Find out:

  - What the SME’s want out of this course?

  - What results do the SME’s want the students to walk away with?

  - Is a formal needs assessment necessary?

  - Who is the target audience? (Identify and analyze learners)

- Determine Course Goals & Objectives

  - Define goals as measurable business metrics

  - Write Terminal Learning Objectives (TLOs)

  - Write Enabling Learning Objectives (ELOs)

- Determine content sources; obtain (or request) course content from SME

- Identify and review resources

H.  Project team will set milestones & major target dates for fielding and handoff.

Milestones should include:

    - Preliminary meetings and progress reviews

    - Development stages

    - Fielding (pilot)

    - Hand Off (from Designer to Course Manager as project lead)

    - Revisions/updates targets

I.  Project Manager will develop a specific On-line work plan:

    - Assign tasks to team members and establish deadlines

    - Provide checklist, set Due Dates, Completion Timelines

    - Use wiki space to share content and document course development

    - Rework/update Plan Checklist as necessary

2.  ADDIE Phase 2: Course Design

- Members of the project team staff, in consultation with and concurrence from the

G9 program proponent, will develop an instructional design document called the course training template. This becomes the road map for the course.  The Project Lead for this phase is the Course Designer.

- Project team will design the course using identified competencies for the target

audience. Most competencies can be found in the PDP function within  http://www.imcomacademy.com.

- The project team will:

        - Plan instructional strategy including user interface and user experience

        - Review and revise objectives (if necessary) (TLOs) and (ELOs)

        - Develop assessment instruments

        - Plan student exercises. Ensure they correspond to learning objectives.

        - Write training template

        - Store training template and course syllabus in Project wiki space

- Outcome of the Design Phase is the completed Instructional training

template design document with concurrence from the G9 program proponent.

3.  ADDIE Phase 3: Course Development

- The project team creates and assembles the content assets outlined in the

design phase.  This is when the course is actually written.  The team will:

- Create storyboards, templates and/or prototypes

- Write and develop content using SCORM authoring tool and create both

SCORM and Section 508 compliant versions

- Develop student activities

- Create demonstrations and scenarios

- Develop discussion points

- Create pre-assessment and post-assessments

- Upload SCORM and Section 508 compliant content to LMS

- As appropriate, project team will request G9 program proponents and Garrison

staff to supply case studies and other relevant resources.   Program proponents or select high performers from the Regions may be content presenters using audio or video assets.

- The course description will be written and posted in LMS. The description should

include test taking policy/review, course prerequisites, outcomes/course objectives, student expectations and student activities/course-work involved, instructor name and credentials, IACET CEUs and ACE awarded (if applicable) estimated time to complete.

- The Course Designer will upload and test course content, create course structure

and menu in LMS.  Course will be set as "inactive" to remain hidden from users.  Permissions will be set in LMS to keep course closed allowing access to only those in Quality Control (QC) review team.

- To ensure Quality Control prior to launch, project team will review and revise

project according to any feedback given by team members, program proponents and Garrison staff.

- The Quality Control process consists of at least three reviews.

  - Use the standard Course Review Form during all reviews (Appendix 3)

  - Conduct initial review individually, evaluating content flow, technical

functionality, readability, grammar and spelling errors and information accuracy.

  - The second review will occur after changes resulting from first review have

been made. The second review will be completed by non-project team members such as other School staff, Service Culture Educators and/or garrison staff volunteers. During this review, care should be taken to ensure that the course is being tested at multiple geographical locations.

  - Project Team members, using the review form, will conduct the final review

individually, after issues identified in second review have been addressed, with a suspense date assigned by the project lead. Each member will track how long it takes to review for CEU calculation.

- Additional quality controls to be completed by Project Team:

- Develop On-line Course Survey and attach survey to course in LMS

- Complete CEU and ACE Accreditation packages, including syllabus

- Store course content package, including all assets and original core

development files (Storyline, Captivate, SimWriter, PP, engage, flash) on School sever located here: www.imcomacademy.com/archives.  Naming convention is course name, last revise date, i.e. Accountability_12Jan2017

4.  ADDIE Phase 4: Implementation Course Delivery & Management

- This is the course delivery phase. The outcome of this phase is a trained student.

- Execute the marketing plan, the project team works on getting the word

out about the course using the following media elements:

- School Newsletter (if applicable)

- IMCOM Academy Homepage

- Integrated communication avenues

- IMCOM Newsletter

- ArmyMWR Webpage

- Service Culture Educators

- Regional SME’s place link on respected Intranet Webpage (if available)

- Marketing to advertise internally and externally

- Project team will request program proponents and Region staff assistance in

identifying students for courses to ensure the correct target audience participation. They can also promote participation at appropriate levels.  If course is required, request G9 develop and communicate guidance regarding mandatory requirement.  This may require writing an OPORD.  For recurring annual course requirement, course will be set up each year with date, Course Name, Date (CYS Accountability and Supervision 2017)
and LMS activity date set from 1 January to 31 December. See CYS Accountability and Supervision as an example.

- Prepare to Launch and set “Go Live” date.

- Program Manager will notify Registrar to open course in course catalog (internal

and external) and to review course description for required elements.

- Initial project leader remains course manager for this initial period

- Branch Chief of Learning Solutions notifies SMEs, internal school staff and

G9  that course is launched.

- The first 3 months the course is “Go Live” and serves as pilot

for online courses.  Project Lead (Designer) works as the course manager and lead for this pilot period.

- Two  weeks prior to the hand off to the Course Manager, the entire project

team will hold a formal meeting to review and identify any problems

- The project team will keep records of all meetings and major actions.

- Ensure wiki course space includes all meeting minutes, QC documents and

course materials

- Confirm course package and associated files are located on School Server

and include current version date.

- Designer (Project Manager), –Course Manager and Registrar will

discuss what they have learned during the pilot period and document for future use.

  - Course glitches

  - Difficulty trends related in end course survey or through help desk requests

  - Post Assessment issues

  - Documentation from initial 3 months, pilot timeframe

L.  Course Management

- Official implementation begins after first three month (pilot).  Project Team

Designer and new Course Manager will meet to hand off Course Management responsibilities.

- At the handoff meeting the following topics will be discussed:

  - Are all corrections complete?

  - Pulse of comfort level with the course

  - Student survey and telephone call issues

  - Feedback to students & student files

  - Review marketing needs

  - Add testimonials

  - Ask SME about any needed revision requirements

  - Registrar will change name of the course manager in the LMS

M.  Use “Collaboration Space” for additional references and communication

with students. Course Manager will set-up and manage this space. Examples of what to include:

  - Rubrics

  - Syllabus

  - Established Blogs

  - Articles and reading

  - Students work - assignments or projects uploaded

  - Shared Best Practices

N.  Course Manager Responsibilities:

- Coordinate G9 SME review of managed courses annually, capture feedback

and recommended changes to include in annual business cases.

- Review course content for changes/updates needed annually and include in

business case (Appendix 5).  Work with Branch Chief and online lead to schedule course updates

- Market and recruit for online courses using mass email, SCEs, flyers,

webpage news articles, garrison and other website announcements and other chosen marketing techniques

- Write a newsletter article or flyer about your course annually or when you

need to communicate changes/updates

- Maintain course CEU packet and update annually upload to wiki CEU space

- Provide and develop materials to support ACE review as required

- Answer student questions and troubleshoot any access problems

- Use online course management space as a repository for course

information (training template, syllabus, rubric, course development/revision documentation, etc.)

- Maintain an email folder with student communication

- Maintain student work in a collaboration space (if not captured within online

course)

- Run 2 reports annually 31 March and 30 September showing enrollments,

completions, in-progress status using online report template (appendix 6) level 1 survey results, trends and comments.  Upload to online course management wiki page located here: https://cloud.mwr.army.mil/wiki/display/Training/Online+Course+Management

Reports are DUE:  31 March (run dates- 1 October through 31 March) and 30 September (run dates- 1 April through 30 September). First report is inputted into  annual Business Cases and uploaded to wiki by 31 March (Site URL: https://cloud.mwr.army.mil/wiki/display/54/Academy+Business+Cases.)

- Work with online lead to develop and send level 3 /4 survey if your course is

assigned

5.  ADDIE Phase 5: Course Evaluation

- Evaluation of the course is present in each stage of course design and

development, as each element is reviewed and critiqued.

- The School uses the four level Kirkpatrick Model to evaluate course outcomes.

- Level 1 (reaction-what students thought and felt about the training),

- Level 2 (learning- what students learned in the course),

- Level 3 (behavior-what new skills or behaviors students can apply on the

job), and

- Level 4 (result-what is the effect on the business or environment as a result of

student’s completing the course.)

- Online course evaluation: The project team will develop an evaluation plan that

includes:

- Level 1 end of course survey which the students must complete before

receiving their certificates. The Course Manager will monitor the surveys bi-weekly and resolve any pressing difficulties identified.

- The course manager monitors student success in completing Level 2

assessments including test re-sets. Should keeps statistics on pass/fail rates.

- Levels 3 / 4 and ROI may be conducted periodically according to the School’s

evaluation plan.  The Course Manager will develop questions and recommend target audience for such evaluations and annotate in annual business case.

- With input from the Program Proponent/SME, the Course Manager will

complete annual Business Case using online business case template by 31 March of current FY.

- The Business Case serves dual roles of Business Case and After Action

Report (AAR). The content items include:

Executive Summary

Background

Course Description

Resource Considerations

Conclusion and Recommendation

Appendix B: Student Feedback

- Upon approval from the School for Family and MWR leadership, the Business

Case will be submitted through the G7 Chain of Command to the G9 leadership for information purposes.

- The Business Case serves to point the way ahead for the online course by

identifying required changes in scope, content, and/or availability.

- Based on the requirements identified, the course will be added to the staff

workload for revision.

D.  Perform Revisions and Updates

Appendix 1: ADDIE Model Instructional Design Flowchart

ADDIE Flow Chart steps

| 1.Analysis: | 2. Design | 3. Develop | 4. Implement | 5. Evaluate |
| --- | --- | --- | --- | --- |
| Discover existing resources Review resources with client Conduct instructional analysis Analyze learners and content Define goals as measurable business metrics Write performance objectives Review performance objectives Revise performance objectives (if necessary) | Plan instructional strategy Choose delivery method Write instructional design document Review instructional design document Revise instructional design document (if necessary) | Develop prototype Review prototype Produce training materials Conduct tabletop review Revise course content (if necessary) Pilot the course Client feedback from pilot | Launch course | Evaluate results Gather feedback from learners Measure improvement and gaps Measure business results Revise course and conduct gap training as needed |

Appendix 2: Project Planner Sample

| Course Name |
| --- |
| Overview notes on course scope, initial ideas, etc. |
| Department X has requested a course on ____________ be developed to address _____________. Initial idea is to incorporate case study simulations using SiFMWRiter. Once the course goes live it will be manadatory for certain employees to complete the training. Anticipate approximately 300-500 students in the first year. Blah, Blah,,,,,Perhaps you could even paste text from email traffic outlining the orignal course request. |
| Project Team |
|  | Name | Email | Phone |
| Primary from Desgin Team (Project Manager) | Gretchen Luongo | gretchen.luongo@us.army.mil | 571-243-3257 |
| Secondary from Desgin Team (if applicable) |  |  |  |
| Instructor/Course Manager |  |  |  |
| Subject Matter Expert |  |  |  |
| ACE Accreditor |  |  |  |
| Other |  |  |  |
| Kick-Off Meeting |
| Meeting Date: 3/25/08 Location: Wood Room |
| The purpose of the Kick-Off Meeting is to bring ALL team members together to come to an agreement on the following: Agenda Items 1. Course Goals & Objectives 2. Obtain Course Content from SME 3. Determine if Need Assement is necessary 4. Set Milestones & Major Target Dates for Fielding and Handoff |
| 1. Course Goals & Objectives (for later use in course Macro) |
| Goal/Objective | Description, notes, or any additional info |
| Teach students to properly complete a DAR. | As identified by the SME this has been an ongoing problem and command has determined online training would best address this need. |
| 2. Course Content |
| Source | Content | Location |
| AR 215-1, Military FMWR Programs and NAF Instrumentalities | Appendix G, G-2: Cash Registers | In-house/Online |
| Cashier Handbook | Locally produced document in use at Fort Loyalty, step-by-step instuctions for FMWR cashiers. | SME will email by Fri 3/28/08 |
| FMWR Basic Manager Course | Module 2: ????? | LMS |
| 3a. Is a Needs Assessment Necessary? | YES |
| Why or why not? | Although some of the needs are clear for this training it was decided by the Project Team to complete a needs assessment to ensure that all needs are addressed by this training |
| 3b. Completing the Needs Assessment (if applicable) |
| Task | Lead | Target Date | Actual |
| Create questions & agree | Project Team | 4/1/2008 | 4/4/2008 |
| Distribute & collect responses | SME | 4/15/2008 |  |
| Coordinate follow up meeting to discuss results | Project Manager | 4/17/2008 |  |
| 4. Milestones & Major Target Dates |
| Task | Lead | Notes | Target Date | Actual |
| MACO Meeting | Design Lead | Draft MACRO for further review by team. Set up meeting. | 5/1/2008 |  |
| Course Design - 1st Draft | Design Lead | Design first draft of course for review by team. | 6/15/2008 |  |
| Quality Control 1 | Design Lead initiates, team participates | Individual reviews of course and changes submitted back to Lead Designer. |  |  |
| Quality Control 2 | Design Lead initiates, team participates | Team review of course and changes submitted back to Lead Designer. | 7/15/2008 |  |
| Quality Control 3 | Design Lead initiates, team participates | Final Team review of course and changes submitted back to Lead Designer. | 7/30/2008 |  |
| Course Survey |  |  |  |  |
| CEU Packet Assembly |  |  |  |  |
| Notify Registrar to put Course Descirption in the catalog. |  |  |  |  |
| Marketing |  | Email, Newsletters, Academy homepage… |  |  |
| Go Live |  |  |  |  |
| Course Hand Off |  |  |  |  |
| 1st AAR Due | Course Manager |  |  |  |

Appendix 3: Standard Course Revision Form

Installation Management Academy, School for Family and MWR

Training Review Document

Course: Course Title

Instructions:  To access the course modules, login to the LMS and search for Add Course Title.  You've been added to the course permissions, along with administrators, for reviewing purposes.

START TIME:

| Lesson | Slide Header Text | Says now: | Should say: |
| --- | --- | --- | --- |
| Home | Objectives page... | Only after you have successfully completed each lesson …. | Only after you have successfully completed each lesson and the post assessment …. |

STOP TIME:

Continued on next page…

- How well were the objectives of the module met:  (1=poor, 5=excellent):

- Did you feel engaged throughout the module: (1=not at all engaged, 5=very engaged):

- How would you rate the technical ease of navigating through the module? (1=poor, 5=excellent):

- How beneficial was the narration of the module? (1=not at all beneficial, 5 = very beneficial) :

- Any other feedback you would like to provide?  Use the space provided below.

Appendix 4:  Training Template

MG Robert M. Joyce Installation Management Academy,

School for Family and MWR

CYS Services Mobilization and Contingency Planning

Course Development Plan (MACRO)

MG Robert M. Joyce Installation Management Academy

School for Family and MWR

2280 Signal Road

Fort Sam Houston, TX  78234

Effective Date:  July 2007

Course Approval Authority:

Army: As authorized by the Division Chief, U.S. Army, MG Robert M. Joyce Installation Management Academy, School for Family and MWR, Fort Sam Houston, Texas 78234

Course Creation Date:  2006-2007

Implementation Date:  July 2007

Approval Date:  July 2007

Course Manager:  Peggy Letizio

Course Designer:  Kim Rodrigues

Course Developer:  Kim Rodrigues & Linda Harwanko

Design and Evaluation Chief:  Janis Smith

Development and Delivery Chief:  Pamela Jones

Change Record

| Item to Change | Description | Date Approved | Date Completed | Name / Initials |
| --- | --- | --- | --- | --- |

I:  General Course Information

- Description:  The CYSS Mobilization and Contingency Planning online course teaches CYSS staff how to ensure continued care and supervision for children and youth during deployments, natural disasters, and other emergencies. Based on the highly-regarded Mobilization and Contingency (MAC) Workbook and consultation with a variety of experts, the CYSS Mobilization and Contingency course is designed as a practical exercise for developing an actual MAC Plan. A student interactively analyzes their local Garrison environment, develops a plan and then learns how to monitor, implement, and evaluate it. Expanded course information includes prevention and containment strategies for a pandemic outbreak. Mobilization and contingency is addressed as a CYSS functional proficiency competency.

- Learning Outcome(s):  At the completion of this course the student will have a working Mobilization and Contingency plan to refer to when faced with a threat.

- Length (Hours):

- Pre-course Assignments (Hours):  NA

- Homework Assignments (Hours):  NA

- Course Length (Hours): 15

- Training Location(s):  www.imcomacademy.com

- Target Audience:  This course is designed and targeted at CYSS Coordinators, Child Development Center, Family Child Care, School Age Services, Middle School/Teen, Outreach and SKIES Unlimited Program Directors and any others who need to develop a solid contingency plan in case of an emergency.

- Constraints and/or Parameters:

- Prerequisites:  NA

- Security Classification:  Unclassified.

- Accreditation:  (if applicable)

- ACE:  www.acenet.edu

- ACE Number:  MMWR-0039

- ACE CREDIT Recommendation:  1 hour

- ACE CREDIT Recommendation Date:  2008-present

- IACET:  www.iacet.org

- Current CEUs:  1.5

- Award Date:  5 Dec 2008

II: Course Synopsis

- This course consists of multiple lessons/topics.  All lessons/topics must successfully be completed and students are required to submit their completed Installation Mobilization and Contingency plan in order to pass this course.

- Instructor to Student Ratio:  NA

- Lessons:

| Topic Title | HOURS |
| --- | --- |
|  | Lecture / Didactic | Lab / Practical | Online | Audio-Visual | Written Test | Practical Test | Other | Total |
| Module 1 |  |  |  |  |  |  |  |  |
| Lesson 1 — The MAC Plan |  |  | 2 |  |  |  |  | 2 |
| Lesson 2 — The MAC Planning Process |  |  | 1 |  |  |  |  | 1 |
| Lesson 3 — Pulling It All Together |  |  | 2 |  |  |  |  | 2 |
| Module 2 |  |  |  |  |  |  |  |  |
| Lesson 1 — Working Your MAC Plan |  |  | 2 |  |  |  |  | 2 |
| Lesson 2 — Planning for Widespread Future Contingencies |  |  | 2 |  |  |  |  | 2 |
| Lesson 3 — Evaluating and Revising your MAC Plan |  |  | 1 |  |  |  |  | 1 |
| Lesson 4 — Stress Experienced by Children |  |  | 2 |  |  |  |  | 2 |
| Lesson 5 — Discover Community Resources |  |  | 1 |  |  |  |  | 1 |
| Final Assignment – Upload Your MAC Plan for Instructor |  |  |  |  |  | 2 |  | 2 |

- Course Length:

| COURSE HOURS | TYPE | TOTAL |
| --- | --- | --- |
|  | Lecture / Didactic |  |
|  | Laboratory / Practical |  |
|  | Online | 13 |
|  | Audio-Visual |  |
|  | Written Test |  |
|  | Practical Test | 2 |
|  | Other |  |
|  | Administrative |  |
| TOTAL INSTRUCTIONAL HOURS |  |
| TOTAL ADMINISTRATIVE HOURS | 2 |

- Course Schedule:  Online course. Students take course on their own schedule.

- Student Materials/Equipment:  Computer with access to www.imcomacademy.com; Installation Mobilization and Contingency plan.

- Student Syllabus:  NA

- Pre-course Assignment(s):  NA

III. Course Module(s)

- Module 1:

- Title: Intro to the MAC Plan

- Module Description:  Students will learn what a Mobilization and Contingency (MAC) Plan is, why the plan needs to be viable, and the importance of planning for mobilization. They will learn about the MAC Plan process, including development, monitoring, implementation and evaluation and understand the complexity of MAC situations and how important a thorough and comprehensive MAC Plan is to the success of dealing with mobilization or an emergency contingency situation.

- References / Regulations:

Title:  US Army Child and Youth Services Installation Mobilization and Contingency (MAC) Plan Workbook

Author:  US Army Child and Youth Services

Publisher Year:  n.d.

Edition:  NA

Volume: NA

ISBN:  NA

Publisher: NA

Quantity:  NA

- Materials/Equipment:  Installation MAC plan,  Computer, Internet, www.imcomacademy.com account

5. 	Terminal Learning Objective:

**Note**See glossary for the various competencies, instructional methods, level of learning and evaluations.

| TLO | Competency | Assessment | Outcome Application | Outcome Assessment |
| --- | --- | --- | --- | --- |
| Examine the CYSS Mobilization & Contingency plan and processes needed to have a thorough and comprehensive MAC Plan in any situation. | Functional Proficiency |  |  |  |

- Enabling Learning Objective:

| ELO | Competency | Instructional Method | Level of Learning | Evaluation |
| --- | --- | --- | --- | --- |
|  |  |  | C | P | A |  |
| 1. Explain the purpose of the MAC plan and why planning for mobilization and contingency situations are important. | Functional Proficiency | Online Lecturette, Knowledge checks, Scenarios and practical application | X |  |  |  |
| 2. Describe the importance of using a team approach. | Functional Proficiency | Online Lecturette, Knowledge checks, Scenarios and practical application | X |  |  |  |
| 3. Define the various types of MAC situations. | Functional Proficiency | Online Lecturette, Knowledge checks, Scenarios and practical application | X |  |  |  |
| 4. Identify the MAC Planning Process phases. | Functional Proficiency | Online Lecturette, Knowledge checks, Scenarios and practical application | X |  |  |  |
| 5. Recognize tasks within each phase. | Functional Proficiency | Online Lecturette, Knowledge checks, Scenarios and practical application | X |  |  |  |
| 6. Illustrate the connection between ICYSE and the MAC Plan | Functional Proficiency | Online Lecturette, Knowledge checks, Scenarios and practical application | X |  |  |  |
| 7. Name the types of MAC Planning Tools that are available | Functional Proficiency | Online Lecturette, Knowledge checks, Scenarios and practical application | X |  |  |  |
| 8. Recognize the importance of having a well developed MAC Plan to use when a crisis arises. | Functional Proficiency | Online Lecturette, Knowledge checks, Scenarios and practical application | X |  |  |  |
| 9. Contemplate and plan for unknown variables to create a successful MAC Plan for future use. | Functional Proficiency | Online Lecturette, Knowledge checks, Scenarios and practical application | X |  |  |  |

- Distribution of Contact Hours:

| Topic Title | HOURS |
| --- | --- |
|  | Lecture / Didactic | Lab / Practical | Online | Audio-Visual | Written Test | Practical Test | Other | Total |
| Lesson 1 — The MAC Plan |  |  | 2 |  |  |  |  |  |
| Lesson 2 — The MAC Planning Process |  |  | 1 |  |  |  |  |  |
| Lesson 3 — Pulling It All Together |  |  | 2 |  |  |  |  |  |

- Module 2:

- Title: Develop the MAC Plan

- Module Description: Students will work through various contingency scenarios identifying required elements for a MAC Plan. Students will learn to identify stress indicators and behaviors expressed in children and how caregivers and parents can help children cope during stressful conditions. Students will identify and compile installation agencies, agency roles, and community resources available to assist in a crisis. Students will compile all information and formulate a workable Installation MAC plan.

- References / Regulations:

Title:  US Army Child and Youth Services Installation Mobilization and Contingency (MAC) Plan Workbook

Author:  US Army Child and Youth Services

Publisher Year:  n.d.

Edition:  NA

Volume: NA

ISBN:  NA

Publisher: NA

Quantity:  NA

- Materials/Equipment:  Installation MAC plan,  Computer, Internet, www.imcomacademy.com account

- Terminal Learning Objective:

| TLO | Competency | Assessment | Outcome Application | Outcome Assessment |
| --- | --- | --- | --- | --- |
| Given the MAC planning Process, develop the Mobilization and Contingency plan for your installation. | Functional Proficiency | Completed MAC Plan |  | Viable MAC plan |

- Enabling Learning Objective:

| ELO | Competency | Instructional Method | Level of Learning | Evaluation |
| --- | --- | --- | --- | --- |
|  |  |  | C | P | A |  |
| 1. Given a variety of contingency scenarios, identify required elements for successful MAC planning | Functional Proficiency | Lecturette, Knowledge checks, Scenarios and practical application | X |  |  |  |
| 2. Consider planning for a widespread contingency threat by working through a Bird Flu Pandemic Scenario | Functional Proficiency | Lecturette, Knowledge checks, Scenarios and practical application | X |  |  |  |
| 3. Relate how CYS fits within the Garrison Emergency Operation Command team and the State and Federal Emergency Operations plan | Functional Proficiency | Lecturette, Knowledge checks, Scenarios and practical application | X |  |  |  |
| 4. Recognize that your MAC plan is a living document requiring frequent evaluation/revision. | Functional Proficiency | Lecturette, Knowledge checks, Scenarios and practical application | X |  |  |  |
| 5. Identify indicators of stress in children. | Functional Proficiency | Lecturette, Knowledge checks, Scenarios and practical application | X |  |  |  |
| 6. Understand strategies and methods used to mitigate stress in children. | Functional Proficiency | Lecturette, Knowledge checks, Scenarios and practical application | X |  |  |  |
| 7. Identify the importance of information on community resources | Functional Proficiency | Lecturette, Knowledge checks, Scenarios and practical application | X |  |  |  |
| 8. Develop a usable reference list of community resources available at your installation | Functional Proficiency | Lecturette, Knowledge checks, Scenarios and practical application | X |  |  |  |

- Distribution of Contact Hours:

| Topic Title | HOURS |
| --- | --- |
|  | Lecture / Didactic | Lab / Practical | Online | Audio-Visual | Written Test | Practical Test | Other | Total |
| Lesson 1 — Working Your MAC Plan |  |  | 2 |  |  |  |  |  |
| Lesson 2 — Planning for Widespread Future Contingencies |  |  | 2 |  |  |  |  |  |
| Lesson 3 — Evaluating and Revising your MAC Plan |  |  | 1 |  |  |  |  |  |
| Lesson 4 — Stress Experienced by Children |  |  | 2 |  |  |  |  |  |
| Lesson 5 — Discover Community Resources |  |  | 1 |  |  |  |  |  |
| Final Assignment – Upload Your MAC Plan for Instructor |  |  |  |  |  | 2 |  |  |

IV.	Grading Policy:

- Minimum Passing Score:  75% (C)

- Minimum Standards:  Students will be required to achieve a grade of C or better in order to pass this course and receive credit for completion. Students are required to send in their updated MAC plan to the course instructor at the completion of the course in order to receive full credit for completion and eligible for ACE recommended credit.

- Instructor Qualifications:  On file

VI. Trainer’s Guides:  NA

Appendix 5:  Online Business Case Template

# Text boxes

ADDIE Instructional Design Method:

Phase 5: Evaluate

ADDIE Instructional Design Method:

Phase 4: Implement

ADDIE Instructional Design Method:

Phase 3: Development

ADDIE Instructional Design Method:

Phase 2: Design

ADDIE Instructional Design Method: Phase 1: Analysis